## Worksheet
# | Task Module | Features To be Implemented | Activities To be Done | App Dev (man-day) | Start Date | End Date | Module Total (man-month)
1 | Requirement Understanding |  |  | 2 | 30/01/2025 | 31/01/2025 | 0.5
1.1 | Project Planning |  |  | 2 | 30/01/2025 | 31/01/2025
1.1.1 |  | Purpose and scope analysis | Define objectives and scope clearly | 1 | 30/01/2025 | 30/01/2025
1.1.2 |  | Project scheduling | Develop scheduling and tracking | 1 | 30/01/2025 | 30/01/2025
1.1.3 |  | Delivery timeline creation | Plan project milestones | 1 | 30/01/2025 | 31/01/2025
2 | Development |  |  | 8 | 03/02/2025 | 13/02/2025 | 1
2.1 | Implement Core Features |  |  | 6 | 03/02/2025 | 13/02/2025
2.1.1 |  | Feature 1: Email Verification | Verify email addresses and send OTPs | 1 | 03/02/2025 | 03/02/2025
2.1.2 |  | Feature 2: Supplier Registration | Create and validate supplier registration forms | 1 | 04/02/2025 | 04/02/2025
2.1.3 |  | Feature 3: Two-Step Verification | Set up reviewer and approver workflows | 1 | 05/02/2025 | 05/02/2025
2.1.4 |  | Feature 4: RFP Management | Develop RFP module and submission flow | 1 | 06/02/2025 | 06/02/2025
2.1.5 |  | Feature 5: Reporting | Design and implement reporting module | 1 | 07/02/2025 | 07/02/2025
2.1.6 |  | Feature 6: Data Visualization | Build data visualization components | 1 | 10/02/2025 | 10/02/2025
2.1.7 |  | Feature 7: Dashboard | Create dynamic dashboards with OWL | 1 | 11/02/2025 | 11/02/2025
3 | Deployment |  |  | 1 | 14/02/2025 | 14/02/2025 | 0.5
3.1 | Set Up Docker and Nginx |  |  | 1 | 14/02/2025 | 14/02/2025
3.1.1 |  | Docker Containerization | Prepare and run Docker containers | 0.5 | 14/02/2025 | 14/02/2025
3.1.2 |  | Nginx Configuration | Set up and configure Nginx for load balancing | 0.5 | 14/02/2025 | 14/02/2025
Name | Shahriar Ahmed
Batch | Odoo
ID | 30204