## Worksheet
# | Task Module | Features To be Implemented | Activities To be Done | App Dev (man-day) | Start Date | End Date
1 | Requirement Understanding |  |  | 3 | 29/01/2025 | 31/01/2025
1.1 | Project Planning |  |  | 3 | 29/01/2025 | 31/01/2025
1.1.1 |  | Purpose and scope analysis | Define objectives and scope clearly | 1 | 29/01/2025 | 29/01/2025
1.1.2 |  | Project scheduling | Develop scheduling and tracking | 1 | 30/01/2025 | 30/01/2025
1.1.3 |  | Delivery timeline creation | Plan project milestones | 1 | 31/01/2025 | 31/01/2025
2 | Development |  |  | 17 | 03/02/2025 | 13/02/2025
2.1 | Implement Core Features |  |  | 17 | 03/02/2025 | 23/02/2025
2.1.1 |  | Feature 1: Email Verification | Verify Email Addresses and Send OTPs | 0.5 | 03/02/2025 | 2025-03-02
|  |  | OTP Validation Mechanism | 0.5 | 2025-03-02 | 2025-03-02
2.1.2 |  | Feature 2: Supplier Registration | Create Supplier Registration Form | 2 | 2025-04-02 | 05/02/2025
|  |  | Form Validation and Data Submission | 1 | 06/02/2025 | 06/02/2025
2.1.3 |  | Feature 3: Two-Step Verification | Setup Reviewer and Approver Workflows | 1 | 07/02/2025 | 07/02/2025
|  |  | Implement Approval Mechanism | 1 | 10/02/2025 | 10/02/2025
2.1.4 |  | Feature 4: RFP Management | Develop RFP Module and Submission Flow | 2 | 11/02/2025 | 2025-12-02
|  |  | RFP Approval and Publishing | 1 | 13/02/2025 | 13/02/2025
|  |  | RFQ Submission and Portal View | 1 | 14/02/2025 | 14/02/2025
2.1.5 |  | Feature 5: Reporting | Design Reporting Module | 0.4 | 17/02/2025 | 17/02/2025
|  |  | Data Visualization for Reporting | 0.5 | 17/02/2025 | 17/02/2025
2.1.6 |  | Feature 6: Data Visualization | Graph View | 0.05 | 17/02/2025 | 17/02/2025
|  |  | Pivot View | 0.05 | 17/02/2025 | 17/02/2025
2.1.7 |  | Feature 7: Dashboard | Create Dynamic Dashboards with OWL | 0.5 | 18/02/2025 | 18/02/2025
|  |  | Integrate Data with Key Metrics | 0.5 | 18/02/2025 | 18/02/2025
|  |  | Responsiveness and Interactive Charts | 1 | 19/02/2025 | 19/02/2025
2.1.8 |  | Testing and Debugging | Testing and Debugging Edge Cases | 3 | 20/02/2025 | 23/02/2025
3 | Deployment |  |  | 17 | 03/02/2025 | 23/02/2025
3.1 | Set Up Docker and Nginx |  |  | 1 | 24/02/2025 | 24/02/2025
3.1.1 |  | Docker Containerization | Prepare and Run Docker Containers | 0.25 | 24/02/2025 | 24/02/2025
|  |  | Deploy Docker Containers | 0.25 | 24/02/2025 | 24/02/2025
3.1.2 |  | Nginx Configuration | Set Up Nginx for Load Balancing | 0.25 | 24/02/2025 | 24/02/2025
|  |  | Configure SSL and Security Settings | 0.25 | 24/02/2025 | 24/02/2025
Total |  |  |  | 21
Name | Shahriar Ahmed
Batch | Odoo
ID | 30204